## Tasks Planned 4 next 2 Weeks
Upcoming Task for next 2 weeks |  |  | 2014-06-23 |  |  | 2014-06-24 |  |  | 2014-06-25 |  |  | 2014-06-26 |  |  | 2014-06-27 |  |  | 2014-06-30 |  |  | 2014-07-01 |  |  | 2014-07-02 |  |  | 2014-07-03 |  |  | 2014-07-04 |  |  | 2014-07-07 |  |  | 2014-07-08 |  |  | 2014-07-09 |  |  | 2014-07-10
|  |  | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS | AK | SS | AS
Project Names | POC (Off-shore) | Tasks
XDPS | Srinivas | Test Cases for 18 Jira tickets | 100% | 100% | [9 empty] | Planned Vacation | [19 empty] | Planned Vacation | Planned Vacation
|  | Update existing Regression Test Suite with new feature and enhancement functionalities |  |  |  | 50% | 100% |  | 50% | 90% |  | 50% | 80%
|  | Sign-off from Sergey and David Hives on XDPS 4.7 test design document | [7 empty] | 10% |  |  | 20%
|  | Planned XDPS 4.7 build deployment in QA environment is on June 26th (EOD). Planned XDPS 4.7 Test Cycle 1 | [13 empty] | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100% |  |  | 100%
Planned XDPS 4.7 Test Cycle 2
Any new patch release (unforeseen task)
Any Content validation request (unforeseen task)
Any Content Push for WOL (unforeseen task)
BPA | Aravind | Update test case document with any recent findings of User Observation issues. |  |  | 60% | 50% |  |  | 50% |  | 60% | 50%
|  | Follow up with Lana on questions related to Updated use cases | [5 empty] | 50%
|  | Send BPA 3.7 test design document for Tech/BA final Review & Sign-off | [8 empty] | 10%
|  | Update Review comments & Complete Test Design document for BPA 3.7 Release | [12 empty] | 100%
|  | Planned BPA 3.7 Build deployment in QA environment is on June 27th (EOD). BPA 3.7 Final Test Cycle will commence from Jun 30th | [15 empty] | 100% |  | 30% | 100% |  | 30% | 100% |  | 100% | 100% |  | 100% | 100% |  | 30% | 100% |  |  | 100% |  | 30% | 100%
Virtual Issue | Aravind | VI importer Test Design document 100% completed and will be signed off by June 20th |  |  | 10%
|  | VI Importer Test Cycle 1 planned start date is on June 27th and end date July 1st | [14 empty] | 100% |  |  | 70% |  |  | 70%
|  | VI Importer Test Cycle 2 planned start date is on July 4th to July 8 (Optional test cycle depends on the no of defects identified in cycle 1) | [29 empty] | 70% | [5 empty] | 70%
|  | Follow up with VI Builder Test Design document related queries and update those in the test design document |  |  | 30% |  |  | 50% |  |  | 30%
Resource Allocation Tallied |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 100% | 100% | 100% | 100% | 100% |  |  | 100%
Additional Tasks:
Jira Access request email sent to John Flint for VI project
Project portal directory access request from John Flint
Follow up with KSM 1.4 & 1.5 schedule and update John flint
Watch - Virtual Issue project schedule change
BPA - Jira Follow up for new user observation. On June 24 please send an email to Ashish joshi, lana, jon, Arindam/rajdeep and find out the final list of jira tickets to be fixed in build version 3.7
All UAT Observations list should be filtered captured in excel sheet and send the final passed list to UAT team.

## XDPS 4.7 Plan
XDPS 4.7 Maintenance Release Timeline/Schedule Plan
Task | No of Days | Start Date | End Date | Resource | My Comments
Test Design Phase: | 6 days
Create Test Plan (update scope and schedule section) | 0.5 | 2014-06-19 | 2014-06-19 | Anuradha Kathirvel
Create Test Scenario/ Create test cases (18 jira tickets) (Enhancement/Task Jira Tickets) | 3 | 2014-06-19 | 2014-06-23 | Srinivas Simakurthi Anuradha Kathirvel
Review and Update Test Design document | 3 | 2014-06-24 | 2014-06-26 | Srinivas Simakurthi
Test Execution Phase:
Test Cycle 1 | 10 days
Smoke Testing | 1 | 2014-06-27 | 2014-06-27 | Srinivas
JIRA tickets testing (total 18 jira tickets) | 5 | 2014-06-30 | 2014-07-04 | Srinivas
XDPS Regression testing (approx. 200 test cases) | 4 | 2014-07-08 | 2014-07-11 | Srinivas | Please make wise decision if any issues found during jira ticket validation and that invokes new QA build then you don't need to do full regression. Just test high risk regression scenarios only for 2 days.
Test Cycle 2 (Optional) | 8 days |  |  |  | No Major issues found in test cycle 1 - Run complete regression and provide sign-off
Smoke Testing | 1 | 2014-07-16 | 2014-07-16 | Srinivas
JIRA Defects which are failed on cycle 1 | 3 | 2014-07-17 | 2014-07-21 | Srinivas
XDPS Regression Testing (approx. 200 test cases) | 4 | 2014-07-22 | 2014-07-25 | Srinivas
Note: This plan is yet to be sent to Sergey and David for review and approval

## Virutal Issue Plan
Task Name | Duration | Start | Finish | Predecessors | Resource Names | My Comments
Functional testing | 120 days? | Tue 2/25/14 | Mon 8/11/14
Functional QA - Knowledge Store Maintenance Release 1.4: (VI Importer) | 12 days | Mon 6/9/14 | Tue 6/24/14 |  | Galina Adamova /Siva
Test Cycle 1 - Testing | 7 days | Mon 6/9/14 | Tue 6/17/14
Smoke and Functional Testing | 7 days | Mon 6/9/14 | Tue 6/17/14
Test Cycle 2 - Testing | 5 days | Wed 6/18/14 | Tue 6/24/14
Smoke and Functional Testing | 7 days | Wed 6/18/14 | Thu 6/26/14
Functional QA - Knowledge Store Maintenance Release 1.5: (VI Builder) | 1 day? | Tue 2/25/14 | Tue 2/25/14
Test Cycle 1 - Testing | 1 day? | Tue 2/25/14 | Tue 2/25/14
Smoke and Functional Testing |  | ?? | ?? |  |  | John Flint is working with Ilshat to find the date for KSM 1.5 build
Test Cycle 2 - Testing | 1 day? | Tue 2/25/14 | Tue 2/25/14 |  |  | Galina should update us with the updated dev plan of KSM 1.5
Smoke and Functional Testing |  | ?? | ??
Functional QA - Virtual Issue 1.0: | 51 days | Mon 6/2/14 | Mon 8/11/14 |  | Vidhya
Test Design - Virtual Issue | 32 days | Mon 6/2/14 | Tue 7/15/14
Requirements Analysis | 5 days | Mon 6/2/14 | Fri 6/6/14
Test Plan | 5 days | Mon 6/9/14 | Fri 6/13/14 | 14,41 | Vidhya Subbaraj
Virtual Importer Functionalities | 10 days | Mon 6/9/14 | Fri 6/20/14
Create Test Scenario/Cases | 7 days | Mon 6/9/14 | Tue 6/17/14 | 41,14,16,19 | Aravind 100%,Anuradha 50%
Review/Update Test Cases | 2 days | Wed 6/18/14 | Thu 6/19/14 | 44 | Aravind 100%,Anuradha 50%
Sign-off from Technical/Business Lead | 1 day | Fri 6/20/14 | Fri 6/20/14 | 45
Virtual Builder Functionalities | 5 days | Wed 7/9/14 | Tue 7/15/14
Create Test Scenario/Cases | 3 days | Wed 7/9/14 | Fri 7/11/14 | 59 | Aravind 100%,Anuradha 50%
Review/Update Test Cases | 1 day | Mon 7/14/14 | Mon 7/14/14 | 48 | Aravind 100%,Anuradha 50%
Sign-off from Technical/Business Lead | 1 day | Tue 7/15/14 | Tue 7/15/14 | 49 | Aravind 100%,Anuradha 50%
Testing Execution | 32 days | Fri 6/27/14 | Mon 8/11/14
Milestone : VI Importer | 8 days | Fri 6/27/14 | Tue 7/8/14
Test Cycle 1: | 3 days | Fri 6/27/14 | Tue 7/1/14
Smoke Testing | 1 day | Fri 6/27/14 | Fri 6/27/14 | 33,46,25 | Aravind 100%,Anuradha 100%
Functional Testing | 2 days | Mon 6/30/14 | Tue 7/1/14 | 54 | Aravind 100%,Anuradha 100%
Development Code Fix (2 days) | 2 days | Wed 7/2/14 | Thu 7/3/14 | 55
Test Cycle 2: | 3 days | Fri 7/4/14 | Tue 7/8/14
Smoke Testing | 1 day | Fri 7/4/14 | Fri 7/4/14 | 56 | Aravind 100%,Anuradha 100%
Defect Fix Validations & Functional Testing | 2 days | Mon 7/7/14 | Tue 7/8/14 | 58 | Aravind 100%,Anuradha 100%
Milestone : 2 VI Builder | 19 days | Wed 7/16/14 | Mon 8/11/14
Test Cycle 1: | 5 days | Wed 7/16/14 | Tue 7/22/14
Smoke Testing | 0.5 days | Wed 7/16/14 | Wed 7/16/14 | 24,50 | Aravind 100%,Anuradha 100%
Functional Testing Virtual Builder | 4.5 days | Wed 7/16/14 | Tue 7/22/14 | 62 | Aravind 100%,Anuradha 100%
Development Code Fix (2 days) | 2 days | Wed 7/23/14 | Thu 7/24/14 | 63
Test Cycle 2: | 5 days | Fri 7/25/14 | Thu 7/31/14
Smoke Testing | 0.5 days | Fri 7/25/14 | Fri 7/25/14 | 64 | Aravind 100%,Anuradha 100%
Defect Fix Validations | 1.5 days | Fri 7/25/14 | Mon 7/28/14 | 66 | Aravind 100%,Anuradha 100%
Regression of Virutal Importer and Virtual Builder | 3 days | Tue 7/29/14 | Thu 7/31/14 | 67 | Aravind 100%,Anuradha 100%
Development Code Fix (2 days) - Optional | 2 days | Fri 8/1/14 | Mon 8/4/14 | 68
Test Cycle 3: (Optional) | 5 days | Tue 8/5/14 | Mon 8/11/14
Smoke Testing | 0.5 days | Tue 8/5/14 | Tue 8/5/14 | 69 | Aravind 100%,Anuradha 100%
Defect Fix Validations | 1 day | Tue 8/5/14 | Wed 8/6/14 | 71 | Aravind 100%,Anuradha 100%
Regression Testing | 3.5 days | Wed 8/6/14 | Mon 8/11/14 | 72 | Aravind 100%,Anuradha 100%

## BPA 3.7
BPA Build 3.7 buildTimeline/Schedule Plan
Task | No of Days | Start Date | End Date | Resource
Test Design Phase: | 6 days
User Observation/Requirement Update Issues (total 38 + expected issues 10 to 15) | 3 | 2014-06-19 | 2014-06-23 | Aravind, Anuradha
Review and Update Test Design document | 3 | 2014-06-24 | 2014-06-26 | Aravind, Anuradha
Test Execution Phase:
Final Cycle 1 | 8 days
Smoke testing | 1 | 2014-06-30 | 2014-06-30 | Aravind, Anuradha
E2E flow | 1 | 2014-07-01 | 2014-07-01 | Anuradha, Aravind
Complete Regression (+ User Observation issue 38) | 4 | 2014-07-02 | 2014-07-08 | Aravind, Anuradha | Note: Aravind planned vacation is on Jul 7
PDF Validations | 1 | 2014-07-09 | 2014-07-09 | Aravind, Anuradha
Reg Migration Tool Validations +Random Comparision of Redcap/Dart vs BPA data | 1 | 2014-07-09 | 2014-07-09 | Aravind, Anuradha