## Daily Report
VID's Team: Daily Tasks & Status Report –27/Mar/2015
Daily Status Report
S. No. | Resources Name | Tasks for Today (pick the task): | Type of Task | Planned for Today | Completed for Today | Issues/Risk | Status | Comments
1 | Anuradha |  |  |  |  | N/A | N/A | Not Available
2 | Aravind | Test Design | XDPS : Test design for Next patch with xDPS-677 is completed and sent to Dev team for review |  | Completed for Today
3 | Srinivas | Test Design | BPA : Review and updation for the build Ver 4.5 with Test cycle 1 is completed and sent to Dev / BA for review |  | Completed for Today | - | -
Test Design
Test Scenario
Test Case Review
Test Case Update
Test Case Execution
Defect Verification/Retest
Common Test Suite preparation
Reading project related documentation
Preparing Presentation
Knowledge Transfer
Regression Testing
Smoke Testing
Requirement reviews
Other